Press Accreditation Strategic Plan

for the Olympic Games LA28

14 to 30 July 2028

Final Version

This page has been left blank intentionally.

Table of Contents

Key Dates - Press Accreditation Timeline	4

1.	Introduction and Roles	7

1.1.	Introduction and Aim	6

1.2.	Participants in the Process	8

1.3.	Accreditation Categories	10

1.4.	The Role of the IOC	14

1.5.	The Role of the OCOG	16

1.6.	The Role of the NOC	17

1.7.	The Role of the IFs	20

2.	Quota, Accreditation Procedures and Timelines	22

2.1.	Quota	22

2.2.	NOC Quota Allocation	23

2.3.	Stage One: PRESS BY NUMBER	25

2.4.	Stage Two: PRESS BY NAME	27

2.5.	Non-Media Rights-Holding Broadcast (non-MRH) Accreditations	27

2.6.	Sports Specialists Quota	31

2.7.	IF Journalist (Es) and Photographer (EPs)	33

2.8.	Organisations not included in the NOC Quotas	34

3.	Co-Host Cities	36

3.1.	Allocation of Ex and EPx accreditations 	36

4.	Working procedures	37

4.1.	IOC Master E Accreditation tracking database	37

4.2.	Working Languages	38

Acronyms	39

Annexes	41

Key Dates - Press Accreditation Timeline - LA28

| 2026 | 12 May 2026 | IOC Press Accreditation Allocation Quota Working Group meeting to establish the “E” press accreditations for the National Olympic Committees (NOCs) for the Olympic Games LA28. Participants to include IOC Media Operations and NOC Relations, the Head of Press Operations LA28 and select representatives. Meeting to be held at the Olympic House in Lausanne. The group will also confirm the allocation of NOC E accreditations per NOC. |
| --- | --- | --- |
|  | July 2026 | IOC notifies all NOCs of their press accreditation allocation for the Olympic Games LA28. |
|  | TBC August to 30 October 2026 | Members of the press seeking accreditation are required to send their expression of interest through the Media Registration Page. This includes applications for non-media rights holding television and radio organisations (non-MRH). The relevant NOC is responsible for managing and responding to the applications from their territory. (Confirmation of requests from non-MRH follow a slightly different process - see later in document). The IOC will not handle any requests received via this platform. |
|  | Week commencing 5 October 2026 | Press by Number Process Starts for NOCs LA28 distributes Press by Number forms and related press publications to NOCs. Non-Media Rights-Holders (non-MRH) Application Process Starts NOCs with non-MRH in their territory interested in covering the Games should submit a long list of recommended non-MRH organisations, if applicable, to the IOC for approval via the Press by Number form. The form will include a separate section for NOCs to submit the non-MRH organisations with clear instructions. |
|  | 18 December 2026 | Press by Number Process Ends for NOCs Deadline for NOCs to return the completed Press by Number forms to LA28 (according to the quota that they received from the IOC in July 2026 and excluding the ENR accreditation quota) and notify the press organisations within their territory of their accreditation allocations and provide instructions on accreditation deadlines and how to reserve press accommodation. Non-Media Rights-Holders (non-MRH) Application Process Ends NOCs must submit non-MRH applications by 18 December 2026. The IOC will review applications and inform NOCs of the outcome the w/c 25 January 2027. Note: ENR accreditation quotas are very limited and approval is not guaranteed. Strict timelines apply. Late submissions will not be accepted. |
| 2027 | Week commencing 18 January 2027 | Press by Number Process Starts for selected IFs LA28 distributes Press by Number forms and related press publications to selected IFs for their sport specialist media. |
|  | Week commencing 25 January 2027 | IOC will notify NOCs about their approved non-MRH applications after reviewing the long list submitted during the Press by Number process |
|  | 12 February 2027 | Press by Number Process Ends for selected IFs LA28 receives completed Press by Number forms from IFs for their sport specialist media. |
|  | Week commencing 18 Oct 2027 | Press by Name Process Starts LA28 distributes the Press by Name materials to NOCs/ IFs and directly accredited organisations that have returned their Press by Number forms and/or have approved ENR accreditation quotas in their territory. The Press by Name process requires NOCs/IFs and directly accredited organisations to gather name/passport/photo and other important information for those to be accredited (includes both press and ENR accreditation) The Press by Name materials are also distributed to directly accredited organisations by LA28. |
|  | TBC | Press by Name User Request Form and Responsible Organisation Undertaking Deadline for NOCs, IFs and directly accredited organisations to return the User Request Form and Responsible Organisation Undertaking to LA28. |
|  | TBC | Press By Name On-line system System opens for NOCs, IFs and directly accredited organisations to submit their details to LA28. |
| 2028 | 18 February 2028 | Press by Name deadline NOCs, IFs and directly accredited press organisations must submit the accreditation applications to LA28 on behalf of their press representatives. |
|  | April 2028 | LA28 distributes the Olympic Identity and Accreditation Cards (OIACs) in the form of Pre-Valid Cards (PVCs) to NOCs, IFs and directly accredited press. |
|  | 14 to 30 July 2028 | Olympic Games LA28. |

# Introduction and Roles

## Introduction and Aim

This document sets out the accreditation framework for written and photographic press as well as non-media rights-holding broadcasters covering the Olympic Games LA28.

It details quotas, policies and procedures, allocation timelines, accreditation categories, access entitlements, eligible persons and identifies organisations that are exempt from National Olympic Committee (NOC) quotas. These are all determined by the International Olympic Committee (IOC). The roles and responsibilities of all parties involved in the process are clearly defined.

The LA28 Organising Committee for the Olympic and Paralympic Games (LA28) administers the process in accordance with the IOC guidelines and schedule but the IOC maintains ultimate responsibility for the process and has final authority.

The press accreditation process for the Olympic Games LA28 is scheduled to start in July 2026, precisely twenty-four months prior to the opening of the Olympic Games, when the IOC will formally notify all NOCs of their allocated press accreditation quotas.  During this time, a media registration page will also be available for interested press to apply.  NOCs will be solely responsible for managing the applications from their territory via this platform.

As per previous editions of the Olympic Games, a Two-Stage Accreditation Process will be implemented, beginning with the Press By Number stage, starting in October 2026.  At this point, LA28 will distribute the Press By Number information and related press publications to the NOCs. The Press By Name stage then follows towards the end of 2027 when the detailed information regarding each individual needs to be submitted for all NOCs and directly accredited organisations.

The IOC will assume responsibility for informing and advising NOCs, International Federations, press organisations and non-media rights-holding broadcast organisations about the procedures, timelines and processes to be adhered to by all parties.

Throughout numerous IOC, NOC, IF and press meetings in 2026 and 2027, the IOC will provide further clarification about the accreditation process and emphasise the importance of complying with the terms and conditions, schedule and deadlines associated with press accreditation.

In parallel, the United States Olympic and Paralympic Committee, (USOPC) in collaboration with LA28, should undertake a similar education initiative for their national media. Comprehensive information on press accreditation procedures will be available on the IOC website as of July 2026.

This document references the accreditation guidelines set out in the “Olympic Games Guide on Media” and the “Accreditation at the Olympic Games Detailed Specifications”, both of which should be consulted alongside this manual.

Both this document and the accompanying timetable are subject to ongoing review, reflecting the dynamic nature of the accreditation process, and flexibility will be essential. Establishing a transparent and cooperative relationship between IOC Media Operations and LA28’s Press Operations and Accreditation departments is vital to the overall success of the programme.

##### Scope

This strategic plan covers accreditation for the written and photographic press as well as non-media rights-holding broadcast organisations (referred to as “E” categories) at the Olympic Games LA28 only.  The process and timetable are supported by relevant IOC departments, particularly the Olympic Games Department, including the Accreditation, Sport and NOC Services functional areas.

The goal of the IOC is to develop a fair and efficient accreditation process for the worldwide press.  This process is designed to support high-quality, comprehensive coverage of the Olympic Games across all territories whilst maintaining a professional working environment for all accredited media representatives.

##### Other Key Points

The media accreditation system ensures efficient and secure access for the large numbers of press at the Olympic Games with other media services relying on its effective management.

Demand for press accreditation at the Olympic Games always exceeds supply, especially in the Host Country. To ensure transparency, the IOC will provide detailed information about the press accreditation procedures on its website and will communicate with key stakeholders on a regular basis.

The IOC aims to ensure that the press accreditation allocation and process is fair and objective.

The IOC will instruct NOCs on a fair and transparent press accreditation allocation.

The OCOG is not authorised to allocate any form of media accreditation except as instructed by the IOC.

All requests for additional accreditations will be dealt with by the IOC.

The main allocation period runs from July to October 2026.  However, late often last-minute, additional accreditations and/or changes will still occur, resulting in extra work for LA28 and the IOC.  Both parties will have procedures in place to communicate changes promptly and efficiently. The accreditation process will continue up to and during the Games.

In accordance with Rule 52 of the Olympic Charter and Section 20 of the Host City Contract, the Olympic Identity and Accreditation Card (OIAC) issued to media personnel along with a valid passport or other travel document, will allow the holder to enter and remain in the Host Country and carry out professional duties related to the Olympic Games for at least one month before and one month after the Olympic Games without the need of a separate visa or work permit.  (To verify given the Games-time visa arrangements to be confirmed by LA28 and the relevant US authorities).

## Participants in the Process

The main participants in the Olympic Games accreditation process are:

The International Olympic Committee (IOC)

The LA28 Organising Committee for the Olympic and Paralympic Games (LA28)

National Olympic Committees (NOCs)

Key stakeholders in the process:

National Olympic Committees (Media Department for large NOCs)

IOC Recognised World News Agencies

Host National News Agency (if applicable)

International press and photographic organisations

US national media

Non-media rights-holding broadcasters (non-MRH)

International Federations (IFs) (Media Departments)

Their roles and responsibilities are detailed in this document.

## Accreditation Categories

##### Written and Photographic Press (E categories)

The written and photographic press, including technicians, support staff and non-media rights-holding radio and television personnel, are accredited to the Olympic Games under the generic category “E”. The categories and descriptions are as follows:

| Code | Description |
| --- | --- |
| E | JOURNALIST: Journalist, editor, photographic editor, employed or contracted by a world news agency, a national agency, a general daily newspaper, a sports daily, a sports magazine or periodical, internet site and social media news site or independent/freelance journalist working under contract. |
| Es | SPORT SPECIFIC JOURNALIST: Journalist specialising in a sport on the Olympic Games programme, meeting the same criteria as those defined for category “E”. Es will include access to all disciplines of that sport. |
| EP | PHOTOGRAPHER: Photographer, meeting the same criteria as those defined for category “E”. |
| EPs | SPORT SPECIFIC PHOTOGRAPHER: Photographer specialising in a sport on the Olympic Games programme, meeting the same criteria as those defined for category “E”. EPs will include access to all disciplines of that sport. |
| ET | TECHNICIAN: Technician, meeting the same criteria as those defined for category “E”. ET accreditations are limited to technical support personnel of major news agencies, organisations and/or photo agencies only and are generally identified by those organisations that rent Rate Card and telecommunications equipment at the Main Press Centre (MPC) and competition venues. |
| Ec | SUPPORT STAFF: Support staff of an accredited press organisation (office assistant, secretary, interpreter, etc). Access to the MPC only. Assigned only to an accredited press organisation, NOC or future Organising Committee of the Olympic Games (OCOG) which has reserved a private office space at the MPC. |
| ENR | NON-MEDIA RIGHTS-HOLDING BROADCAST ORGANISATION: Non-media rights-holding radio and/or television organisation (non-MRH). ENR accreditations are only allocated by the IOC in close consultation with the NOC. It is strictly prohibited for an NOC to grant a member of a non-MRH organisation any type of E accreditation. |
| NOC E | PRESS ATTACHE: Press Attaché looking after the NOC’s athletes and/or producing written (excluding audio/video) content for the NOC’s official platform for editorial purposes only. |
| NOC Es | PRESS ATTACHE: Press Attaché looking after the NOC’s athletes and/or producing written (excluding audio/video) content for the NOC’s official platform for editorial purposes only. NOC Es accreditation is sport specific and covers one single sport, including all disciplines of that particular sport. |
| Ex | LOCAL PRESS: Journalist of the local press (the definition of local press is determined jointly by the IOC, the NOC of the host country and the OCOG). |
| EPx | LOCAL PHOTOGRAPHER: Photographer of the local press (the definition of local photographer is determined jointly by the IOC, the NOC of the host country and the OCOG). |

- “E” accreditation entitlements and access

| - Category | - Venue Access | - Zone Access | - Seating Access | - High Demand Events | - Transport |
| --- | --- | --- | --- | --- | --- |
| - E | - ALL, MPC - OLV with guest pass | - 4 - White | - Seating in “E” Stand | - With complimentary ticket (limited numbers) - Seat in “E” Stand | - T-C |
| - Es | - Own sport venues, MPC - OLV with guest pass | - 4 - White | - Seating in “E” Stand | - With complimentary ticket (limited numbers) - Seat in “E” Stand | - T-C |
| - Ex | - Relevant local venues - OLV with guest pass | - 4 - White | - Seating in “E” Stand | - *With complimentary ticket (limited numbers) - Seat in “E” Stand | - T-C |
| - EP | - ALL, MPC - OLV with guest pass | - 4 - White | - Access to photo positions with special vest/bib/armband | - With complimentary ticket (limited numbers) - Field access with special vest/bib/armband - No seating provided | - T-C |
| - EPs | - Own sport venues, MPC - OLV with guest pass | - 4 - White | - Access to photo positions with special vest/bib/armband | - With complimentary ticket (limited numbers) - Field access with special vest/bib/armband - No seating provided | - T-C |
| - EPx | - Relevant local venues - OLV with guest pass | - 4 - White | - Access to photo positions with special vest/bib/armband | - *With complimentary ticket (limited numbers) - Field access with special vest/bib/armband - No seating provided | - T-C |
| - ET | - ALL, MPC - OLV with guest pass | - 4 - White | - No seating access. Access to photo positions and “E“ Stand for technical reasons | - With complimentary ticket (limited numbers) - Access to photo positions and “E” Stand for technical reasons only | - T-C |
| - Ec | - MPC | - n/a | - No seating access | - No seating access | - T-C |
| - ENR | - ALL, without equipment MPC - OLV with guest pass without equipment | - 4 - White | - Seating in “E” Stand | - With complimentary ticket (limited numbers) - Seat in “E” Stand | - T-C |
| - **NOC E | - ALL, MPC - OLV with guest pass - MZ (athlete’s side of the Mixed Zone) | - 4 - Blue | - Seating in “E” Stand | - With complimentary ticket (limited numbers) - Seat in “E” Stand | - T-C |
| - **NOC Es | - Own Sport Venue, MPC - OLV with guest pass - MZ (athlete’s side of the Mixed Zone) | - 4 - Blue | - Seating in “E” Stand | - With complimentary ticket (limited numbers) - Seat in “E” Stand | - T-C |

- *To be decided closer to the Games if Ex and EPx will receive high demand event tickets.

**This NOC E / NOC Es category will continue to fall under the responsibility of IOC Media Operations; however, it will be classified within the NOC category (green).

##### Eligible Persons

All E category accreditations are granted exclusively to media professionals who satisfy the eligibility requirements outlined in section 1.3.

The following individuals or entities listed below do not qualify for press accreditation:

- Publishers and marketing personnel

- Athlete management companies

- Individuals representing athletes

- Advertising, public relations and promotion agencies

- Commercial partners associated with NOCs

- Government ministries or organisations

The IOC has established press accreditation terms and conditions that must be reviewed thoroughly in conjunction with any press accreditation that is awarded.  This document is currently under review.  The main areas that this document covers are as follows:

- Guidelines on how press accreditations are distributed by NOCs.​

- Press by Number Control measures.​

- Quota allocation and use of NOC E.​

- No show policy.​

- Code of Conduct for accredited photographers along with guidelines for NOCs on selecting photographers​.

## The Role of the IOC

“All decisions concerning the coverage of the Olympic Games by the media rest within the competence of the IOC.” Olympic Charter 48 2

“The Olympic Identity and Accreditation Card is delivered, under the authority of the IOC. It gives access, to the degree necessary and as indicated thereon, to the sites, venues and events placed under the responsibility of the OCOG.” Olympic Charter 52 3

“Accreditation is not a right and is granted or withdrawn solely at the IOC's discretion. The OCOGs, IFs, NOCs and all other persons or parties concerned must comply with all regulations, decisions, manuals, guidelines and instructions regarding accreditation.” Olympic Charter 52 2

##### Press Accreditation

The IOC sets the press accreditation framework to fit the host country's conditions, including policies, procedures, quotas, categories, access rights, eligible individuals and confirmation of organisations not subject to NOC quotas.

The IOC approves all forms and documentation related to the press accreditation process.

The IOC determines the number of media representatives accredited to cover the Games and the access entitlements granted. It also exclusively reserves the right to refuse, suspend or cancel an accreditation.

IOC Media Operations is the department responsible for managing the press accreditation process within the IOC and will be the point of contact and decision maker within the IOC on matters related to press accreditation. LA28 Press Operations will be its key contact within LA28 and the LA28 Accreditation team will also work closely and often directly with IOC Media Operations.

The IOC Media Operations department acts in accordance with the accreditation principles laid down by the IOC Executive Board, whose decisions are final.

##### Allocation

The IOC Press Accreditation Allocation Working Group, with the OCOG Head of Press Operations, establishes E category accreditation quotas for each NOC (excluding ENR accreditation quotas), according to the overall IOC quota.

The IOC deals directly with the accreditation allocation for:

The IOC-recognised world news agencies:

- Agence France-Presse (AFP)

- The Associated Press (AP)

- Reuters Limited

- Xinhua News Agency.

The host national agency of the host country (if applicable).

The official photographic agency of the IOC (Getty Images).

A limited number of international news organisations which do not fall within the territory of any NOC, at the sole discretion of the IOC.

Olympic publications specialising in covering the Olympic Games only.

Non-media rights-holding radio and/or television news organisations (non-MRH) in close consultation with the NOC (please see detailed process later on in this document).

Written and photographic sport specialists covering a sport on the Olympic programme that have not been included in the NOC allocations, in collaboration with certain International Federations not included in NOC quota.  This is typically applicable when the competition venues are located outside of the host city (to be discussed later in this document).

IF staff journalists and photographers of sports on the Olympic programme.

The IOC reserves the right to include, at its discretion, any organisation whose representatives meet the established criteria and conditions.

The IOC, LA28 and the USOPC will jointly determine the need for an allocation of Ex/EPx categories and will agree on the criteria, quotas, categories and access entitlements.

LA28 handles the press accreditation process but the IOC is responsible for the final approval of all accreditations. Any additions or amendments requested by an NOC or individual must be referred by the OCOG to the IOC Media Operations Department, which will advise LA28 of its decision.

## The Role of the OCOG

The OCOG acts in accordance with the instructions and guidelines it receives from the IOC. In matters of accreditation, the OCOG is the principal coordinator and primary partner of the IOC.

The Los Angeles Organising Committee (LA28) must prepare accreditation forms and publications for the E categories. The OCOG will receive certain compulsory information requirements from the IOC.  All documents need IOC approval.

LA28 is responsible for sending all accreditation documents to the NOCs and organisations or individuals designated by the IOC.

LA28 is not authorised to allocate or change any type of media accreditation except as instructed by the IOC.

LA28 will verify data application forms and inform the IOC of any discrepancies. During the Press by Name process LA28 will send a weekly, updated and detailed status report to IOC Media Operations (format to be provided by the IOC).

LA28 shall provide full updates of its media accreditation database to the IOC upon request.  This includes supplying the IOC with a complete LA28 press accreditation database in a format specified by the IOC on the day of the Closing Ceremony.

LA28 Press Operations will be the key contact within LA28 for the IOC, the press and NOCs on matter of press accreditation, working closely with the LA28 Accreditation Department. LA28 ACR and LA28 PRS will not be permitted direct communication with the NOCs without initial communication/introduction from NCS.

The OCOG is solely responsible for dispatching all pre-valid OIAC to all accredited press organisations and individuals: This includes:

To all NOCs, who are responsible for distributing to their national press, non-MRHs (as agreed with the IOC) and their NOC E press attachés.

To all IOC recognised world news agencies directly accredited by the IOC.

To all international news organisations directly accredited by the IOC.

To all sports specialists/individuals/freelancers directly accredited by the IOC.

To all IFs, and, where relevant, the IFs with a sport-specific allocation who are responsible for distributing to each individual accredited sport-specialist.

## The Role of the NOC

The NOC is responsible for distributing the press quotas allocated by the IOC within its recognised territory.

Each NOC will establish the quota allocation for each accreditation category. NOCs who have been granted a large accreditation quota should allocate between five and ten per cent of their overall quota for allocation to sport specialist journalists and photographers residing in their country.

Each NOC must allocate quotas strictly in accordance with the IOC’s determinations for each category. Requests to re-allocate quotas require written approval from IOC Media Operations.

If an NOC reallocates quotas not in accordance with their assigned quota (e.g., substituting an ET for an EP without IOC approval) the IOC may not approve the accreditation, or may withdraw it from that NOC.

NOCs should consider the following hierarchy and priorities when allocating their quota:

National news agency

National sports agency

General daily newspaper

Sports daily

Single sport or multi-sport specialist magazine, sports internet site

General information magazine and general news internet sites

NEW!  Media Registration Page

Starting from LA28, the IOC (via Deloitte and LA28) will implement a media registration page. Media organisations wishing to obtain press accreditation to cover the Games for LA28 should submit their requests through this platform.​ This initiative aims to ensure a consistent, fair and transparent press accreditation process across all territories.​The link will be available on www.olympics.com from August (date TBC) until 30 October 2026. NOCs must communicate this link with their national press when they launch their press accreditation process.​

Each NOC will have access to the back end of the platform and will be solely responsible for handling ALL requests originating from their own territory only.​ The NOC will remain responsible for the management of these requests.​ Whilst the IOC will have visibility of the requests, it will not be involved in managing, performing quality control or engaging with any of the media outlets that apply.​

The Press by Number and Press by Name procedures will continue to follow the same process as per previous Games, based on the quota assigned by the IOC in July 2026, and will be managed by the OCOG.  However, LA28 ACR will start discussions with Deloitte to streamline the Press by Number process via the accreditation system rather than sending out Excel templates to NOCs.

The NOC is responsible for distributing, collecting and returning accreditation information from the news organisations to LA28 based on its allocation list within its territory.

The NOC and LA28 also inform their press that the following guides are available on the OCOG’s extranet: Olympic Press by Number Guide, Press Accommodation Guide, Customs and Freight Forwarding Guide, Press Rate Card and Media Facilities and Services Guide. Each individual news organisation is then responsible for returning the accommodation and rate card orders to the OCOG if applicable.

The IOC and LA28 will review and validate the NOCs’ Press by Number forms to ensure quota compliance and that bona fide media organisations have been accredited according to the Press Accreditation Terms and Conditions. To facilitate this, LA28 will upload all Press by Number forms to a shared Sharepoint site (or via the new system) for the IOC to review promptly upon receipt.

The IOC will inform the NOCs of any concerns or discrepancies and may reject applications without re-allocation.

NOC E Press Attaché

Starting with Paris 2024, the IOC introduced the “NOC E” press accreditation category for NOC press attachés.

Individuals serving primarily as press attachés who do not fall within the NOC's quota for "Ao press attaché" may be accredited as NOC E.

The "NOC E" press attaché accreditation provides access to the Mixed Zone via the code MZ. Including the "MZ" designation on the OIAC is optional for NOC E Press Attachés. Similarly, Ao Press Attachés will have Mixed Zone access, as their OIAC will automatically feature the "MZ" entitlement code.

The NOC E category must be used for all NOC press attachés and NOC Communications staff responsible for producing written content (excluding audio or video) for their NOC’s official platform (website, publications etc).  NOCs must not grant any other type of accreditation, including E or EP, to NOC press attachés or NOC Communications staff.

National Federations are only eligible for NOC E accreditation if officially serving as press attachés for their sport for their respective NOC.

NOCs must be able to provide, if requested by the IOC, an assignment letter or an official email from the NOC’s Communications Director and / or the General Secretary detailing the role of the press attachés or editorial staff members.

The “NOC E” press attaché quota will remain within the overall press quota of 6,000 but will be issued under the NOC category (OIAC with a green category background).

*Please note that NOC E applicants are required to sign the Conditions of Participation Undertaking.

The NOC E category has been created so that the entirety of E accreditation allocations can be reserved for professional journalists from news organisations whose role is to ensure maximum coverage of the Olympic Games.  For this reason, the IOC will carefully monitor the use of the NOC E accreditation.  If the NOC does not have any press organisations from their territory interested in covering the Games the NOC E quota will be reduced and kept to a minimum.  If an NOC does not have competing athletes at the Games, then they will not be entitled to an NOC E or an EP accreditation. NOCs will be entitled to 1 E accreditation if they have interested reputable press organisations wishing to cover the Games.

##### NOC E Press Attaché Entitlements

Please see below the entitlements for the NOC E press attaché category:

- All competition venues (Zone 4) (except in cases where the individual is accredited under an NOC Es sport specific category: in which case access will be provided only to the relevant sport)

- *Mixed Zone (MZ) – athlete’s side, with “MZ” code on OIAC

- Main Press Centre (MPC)

- Olympic Village Plaza – with guest pass

- E Stand

- Transport Connect (TC)  - depending on the transport system of the current Games

The NOC press attaché is responsible for all matters related to its own media and the IOC will address issues with the press attaché rather than the individual media concerned.

NOC E Allocation

The NOC E quota has steadily increased with every edition of the Games.​ To manage these numbers and ensure that the majority of accreditations are allocated to media professionals, the quota will be calculated exclusively using a fixed formula based on the number of athletes and sports per NOC.  An NOC participating in a single sport will be allocated one sport-specific NOC E only. IOC Media Operations collaborates with NOC Relations on this methodology. ​

NEW! Although the number of NOC E quotas will decrease for larger NOCs, the NOC E accreditation will become transferable from LA28 onwards.

Furthermore, if NOCs do not have any qualified athletes at the Games, they should not be entitled to an NOC E press accreditation quota. However, the NOC would be entitled to receive press accreditation (E) for any press organisations who would be interested in covering the Games

The IOC always advises NOCs to prioritise their own media for press accreditation, especially when quotas are limited, instead of allocating spots to NOC press attachés.

Please note the following text from the Olympic Charter, Bye-law to Rule 48

“Only those persons accredited as media may act as journalists, reporters or in any other media capacity. Under no circumstances, throughout the duration of the Olympic Games, may any athlete, coach, official, press attaché or any other accredited participant act as a journalist or in any other media capacity.”

Gender Equality

In alignment with the IOC’s ongoing commitment to gender equality, the IOC has been actively developing initiatives to encourage press organisations to increase the representation of female reporters, editors and photographers within their accredited teams at the Olympic Games—particularly within the National Olympic Committees (NOC) quotas.

To support this objective, IOC Media Operations has established a dedicated Gender Equality Working Group within the IOC Press Committee. This group has spearheaded several initiatives, including the planning of educational workshops in 2027 and 2028 aimed at raising awareness amongst NOCs about the importance of promoting gender equity in their press allocations wherever feasible. The IOC also sets aside press accreditation quotas specifically for female journalists who are not selected by their respective NOCs.

## The Role of the IFs

##### Introduction

Historically, the International Federations have not held a specific overall role or responsibility in the press accreditation process for the Olympic Games. However, the IOC acknowledges the International Federations' experience and knowledge of the specialist media covering their respective sports and collaborates with them during the press accreditation process to maximise opportunities for specialist media to cover their sports at the Olympic Games.

##### Sport Specific press and photographers

The IOC has established a specific category of accreditation for journalists “Es” and photographers “EPs” who specialise in covering a particular sport or discipline. The IOC will work with the International Federations to assist, where possible and reasonable, in gaining accreditations for their sports’ key specialist press, if they have not been included in the NOC quota.

This process can apply to specific sports and IFs with a large contingent of sport specialised media. The concerned IFs and quotas still need to be confirmed for LA28 but at previous Games this has included golf, equestrian, basketball and athletics. The IOC also works directly with IFs to allocate a small number of press accreditations if their sport/venue is outside the Host City (i.e. football cities).

Procedure for Sport Specific allocations by the IF

Similar to the NOC process with their affiliated organisations, the IFs will be responsible for their accreditation allocation and application submission process for sport specialist written and photographic press representing media organisations/individuals from their respective sports. This process was successfully implemented for the first time during the Paris 2024 Olympic Games with the selected IFs taking responsibility for their quota and working directly with the OCOG Accreditation department.

Note: The IFs should allocate these Es/EPs accreditations to external sports specialists organisations and freelancers who meet the criteria outlined earlier in the document.  IFs should not allocate this quota to IF staff /communication team members, non-MRH organisations or IOC recognised agencies or international news organisations.  IOC Media Operations will check the lists to ensure compliance with these guidelines. The process is outlined under section 2.6.

##### IF Staff - Journalist and Photographer

The IOC allocates one Es and one EPs accreditation to each IF to assist in written and photographic coverage of their sport, with additional accreditations for sports with multiple venues or disciplines. These accreditations are granted only for journalists and photographers working on an exclusive basis for the IF to assist in sourcing material for the IF’s own editorial purposes.   They must not be granted to freelance journalists or photographers working independently at the Games.

Access for the IF journalist and photographer is limited to the MPC and the venue(s) where their sport is held.  Opening and Closing Ceremonies will be high demand events and will need a ticket (to confirm if IFs will be entitled to receive this ticket nearer to the Games). They will also have access to TC transport.

The IF photographer will be considered as a member of the pool and will be granted pool access privileges at the sport or discipline concerned, in accordance with IOC instructions.

However, all images taken will be for the exclusive use of the IF for editorial purposes only. The photographer is prohibited from entering into agreements with any third-party organisation, photo agency or news organisation to sell, publish or distribute the images.

# Quota, Accreditation Procedures and Timelines

## Quota

The IOC sets the overall quota for “E” category accreditations for each Olympic Games. It is determined following the previous edition of the Olympic Games or Olympic Winter Games.

The quota for the total number of the E accreditations for the Games of the XXXIII Olympiad in Los Angeles will be 6,000.  Accreditations for any Ex/EPx local media will be assessed independently of this quota.

## NOC Quota Allocation

| Step | Description |
| --- | --- |
| 1 | January 2026 The IOC will finalise the Press Accreditation Strategic Plan with LA28. |
| 2 | 12 May 2026 The IOC, together with the IOC Press Accreditation Allocation Working Group, which includes the LA28 Head of Press Operations, select representatives of the IOC Press Committee and IOC Administration, establishes each NOC’s quota for E category accreditations (not including ENR accreditation quotas). This is based on the overall quota of 6,000 accreditations which includes the NOC E press attaché category. Quotas for each NOC are determined using the following criteria: - Number of athletes from the NOC who participated in the previous two Summer Olympic Games - Number of sports participated in by the NOC in the previous two Summer Olympic Games - Number of medals won by the NOC in the previous two Summer Olympic Games - Number of E accreditations allocated in the previous two Summer Olympic Games - Proximity to the host country - Other socio-economic criteria |
| 3 | July 2026 The IOC notifies each NOC of its press accreditation allocation, outlining procedures and deadlines for LA28 which will also be published on www.olympics.com. The OCOG must also include the link in the Press by Number Accreditation Guide and make it available on the OCOG’s Press Operations extranet. The IOC works with the IOC-Recognised world news agencies and the IOC photographic agency Getty Images, to establish their indicative accreditation allocations for LA28 prior to the NOC allocation meeting (March /April 2026). These agencies then have the opportunity to inspect various media accommodation options in Los Angeles and confirm their accommodation preferences and the number of beds needed with LA28. The number of beds should always match the number of press accreditations granted. Other major press organisations that attend the World Press Briefing in July 2026 also have the opportunity to indicate their preferred accommodation preferences to LA28. Their accommodation preferences, and the number of beds required, are confirmed after the distribution of the Accreditation (Press by Number) and Accommodation Guides (see following). |
| 4 | (Date TBC) August 2026 to 30 October 2026 As previously stated, the IOC will announce the press accreditation process on olympics.com in July 2026. For LA28, media should express their interest via the new Media Registration Page. NOCs must inform their national press about this link when launching their own process. NOCs will have access to all accreditation requests originating from their territories and will be solely responsible for managing these applications. In this phase, the IOC’s role will be limited to monitoring the requests; it will not handle or verify any individual applications. The platform will close on 30 October 2026, and it is essential that all applications are submitted before this deadline. NOCs should ensure they thoroughly review and manage all submissions from their respective territories by the close of the platform. |

## 2.3.  Stage One: PRESS BY NUMBER

| Step | Description |
| --- | --- |
| 1 | Week commencing 5 October 2026 - PRESS BY NUMBER STARTS The two-stage press accreditation process begins the week commencing 5 October 2026. LA28 will distribute the Press by Number accreditation forms and the Olympic Press by Number Guide to all participating NOCs. The distribution method is yet to be determined for LA28. - The Press by Number form is a pre-populated form listing the number of press accreditation per category (e.g. “NOC E”, “E”, “EP”, “ET”, etc.) allocated by the IOC and distributed to NOCs only. - This information cannot be modified by the NOC. - NOCs should indicate which media organisations will receive accreditation strictly adhering to the quota allocated by the IOC and in line with conditions outlined in the Press Accreditation Guide provided by the Organising Committee and the IOC guidelines. - The completed form must be submitted to the Organising Committee by the specified deadline. - All forms must be completed with all the information requested. Incomplete forms will be returned to the NOC. The guides below will also be sent with Press by Number forms. Press Accommodation Guide Customs and Freight Forwarding Guide Press Services and Facilities Guide *Press Rate Card Guide (could be dispatched in Nov 2026 depending on approval process timelines) The IOC must approve the accreditation forms and all press documents before publication. These documents must be sent to the IOC in advance, allowing no less than three weeks for review and comment. Each NOC allocates its press accreditation quota to major press organisations in its country and manages the distribution, collection and return of accreditation forms to the OCOG. NOCs also distribute guides from LA28 to accredited media. However, each individual news organisation is responsible for submitting accommodation forms and placing Press Rate Card orders for both space and rental items directly with LA28. |
| 2 | Deadline 18 December 2026 - PRESS BY NUMBER ends NOCs must submit complete Press By Number forms to LA28 by this deadline. All fields must be completed, including the full contact details and the website URLs of each affiliated press organisation and not the contact details of the NOC. (unless it is for the NOC E category). Please refer to Press by Number from Milano Cortina 2026. Incomplete forms will be rejected. The IOC may request additional documentation from NOCs to support and validate their proposed affiliated organisations (e.g. press card, assignment letter in case of doubt). All submitted forms should be promptly uploaded to a Sharepoint site by LA28 for the IOC to review, depending on how the Press by Number is distributed. LA28 will also check the Press By Number forms to ensure each category is in line with the IOC quotas, that organisations receive the correct accreditation (see below) and that the correct organisations have been accredited. Important Allocation Reminders: - E accreditations are for press organisations only, not NOC press attachés or NOC staff producing written content - NOC E accreditations are for press attachés or NOC staff producing written content only, not press organisations - Non-Media Rights-Holding organisations (non-MRH) may only receive ENR accreditation. They cannot receive any other type of accreditation i.e. E, EP, ET or EC accreditation. - If a non-MRH decides to apply for Media Rights-Holder accreditation, then they should automatically renounce their ENR accreditation. Non-MRH cannot have both ENR and MRH accreditation. - Government officials or ministries are not eligible for press accreditation and will be automatically rejected if an NOC attempts to allocate to them. (see full list of ineligible organisations under Section 1.3) LA28 informs the NOC and/or IOC of any discrepancies. The IOC reserves the right to reject applications without re-allocation if the proper procedure has not been followed. |
| 3 | Mandatory IOC Approval IOC Media Operations needs to approve all Press by Number forms. The IOC examines requests from NOCs for additional allocations and determines on a case-by-case basis whether to grant further accreditations, notifying the OCOG of its decision. |

Note: All organisations and individuals directly accredited by the IOC should receive, via the Press Operations extranet, the Press Accommodation Guide, Press Rate Card Guide, Customs and Freight Forwarding Guide and Press Services and Facilities Guide from LA28. These organisations, however, do not need to complete the Press by Number Accreditation process. This is only for NOCs and the IFs with sport-specialist Es/EPs quotas.

## Stage Two: PRESS BY NAME

| Step | Description |
| --- | --- |
| 1 | Week commencing 18 October 2027 - PRESS BY NAME STARTS LA28 provides the Press by Name Accreditation Guide to NOCs that have submitted their approved Press by Number forms, as well as all IOC directly-accredited organisations and IFs. The IOC must approve the Press Accreditation Manual, data fields and form layout (as displayed in the accreditation system) and any other press documentation before publication. NOCs/IFs distribute data requirements to each accredited press organisation, which then submits the names and details of their accredited individuals to the NOC/IF by a specified deadline. The NOC/IF reviews this information and submits it to LA28. This information must align with the approved organisations and categories from the Press by Number stage. |
| 2 | TBC 2027 (date to be confirmed by LA28 Accreditation) On-line system for Press by Name applications opens for NOCs, IFs and directly accredited organisations |
| 3 | 18 February 2028 - PRESS BY NAME ENDS NOCs, IFs and all directly accredited press organisations return the completed Press by Name accreditation applications to LA28 within the required deadline. Timely submission is essential to ensure the pre-valid OIAC is sent before the Games. |
| 4 | February – April 2028 LA28 reviews and confirms the data submitted during the Press by Name process. |
| 5 | No later than April 2028 The LA28 Accreditation Department distributes the pre-valid Olympic Identity and Accreditation Cards (OIAC) to National Olympic Committees, IFs and IOC directly-accredited organisations. NOCs (and relevant IFs) distribute the OIACs to the accredited press organisations. All requests for extra accreditations or changes during press accreditation must be sent by LA28 to the IOC Media Operations Department, which will make the final decision and inform LA28. |
| 6 | 14 to 30 July 2028 Olympic Games LA28. |

## Non-Media Rights-Holding Broadcast (Non-MRH) Accreditations

To meet the Olympic Charter's requirements for comprehensive news coverage, the IOC grants a limited number of ENR accreditations to non-media rights-holding radio and TV broadcasters (non-MRH).  The quota for the Olympic Games LA28 will be approximately 350 to 400 individuals from around 200 non-MRH organisations. This quota is included in the overall quota of 6000 E category accreditations.

Non-MRH organisations must abide by the IOC News Access Rules (NAR) and sign an Undertaking on behalf of the organisation and all persons appointed by the organisation to cover the Olympic Games. IOC Media Operations is responsible for sending and receiving the signed ENR Undertaking. These rules are designed to protect the exclusive rights granted to the media rights-holders (MRH) whose contributions play a key role in funding the Olympic Movement and the development of sport worldwide. Any breach of the News Access Rules will be taken very seriously and may lead to loss of accreditation. The NAR will be published on olympics.com approximately one year before the Games.

NEW!

Following the recommendation of the IOC Press Committee Working Group in 2023, there has been a minor change to the ENR accreditation process effective from the Olympic Winter Games Milano Cortina 2026.

The application process is briefly outlined as follows and explained in detail in the table below:

- Non-MRH organisations submit their applications to their NOCs

- The NOC evaluates all applications and submits a priority long list to the IOC.

- The IOC reviews the applications and may reject applications that do not meet the standards.

- The NOC informs each non-MRH applicant of the IOC’s decision. The NOC and LA28 must ensure that all non-MRH are aware of the respective timelines for press accommodation and all press services guides.

- The NOC acts as the Responsible Organisation for submitting ENR accreditations during the Press by Name stage alongside their respective E, EP, EC and ET allocations.

Non-MRH Allocation Reminders:

- An NOC is not permitted to grant any form of press accreditation (such as E or EP) to a member of a non-MRH organisation without prior approval from the IOC.

- Independent filmmakers, documentary producers and production companies are not eligible and are not accredited by the IOC.

- Priority is given to non-MRH organisations with a national rather than a regional focus with exceptions for regional outlets from the host country.

- Media Rights-Holders (MRH) cannot receive ENR accreditations.

- Up to three people from each non-MRH organisation may be accredited, with certain exceptions for certain organisations (e.g., CNN).

- The IOC allocates ENR accreditations directly to some non-MRH organisations with an international focus (e.g. CNN).

| Step | Description |
| --- | --- |
| 1 | From August to October 2026 NOCs should inform non-MRH organisations in their territory seeking ENR accreditation to express their interest through the Media Registration Page |
| 2 | 18 December 2026 Non-MRH Deadline NOCs must submit a long list of recommended non-MRH, where applicable, to the IOC for approval. The submissions must be sent to the IOC via the Press by Number form. All submissions must be received by 18 December 2026. Strict timelines apply. Late submissions will not be accepted. IOC-Recognised world news agencies that have broadcasting platforms will receive their quota from the IOC prior to this date (along with their E allocation) in order to facilitate accommodation bookings. |
| 3 | ENR Accreditation Approval Week commencing 25 January 2027, the IOC will notify NOCs of the approved non-MRH organisations in their territory (where applicable), including accreditation numbers. Subsequently, the IOC will compile and provide LA28 with a database of all approved ENR organisations and their contact details as well as the corresponding NOC details. The respective NOC is responsible for informing all non-MRH organisations about press accommodation procedures and the published guides as listed below, as received from LA28: Press Services and Facilities Guide Press Accommodation Guide Customs and Freight Guide Press Rate Card Catalogue |
| 4 | All accredited non-MRH must sign the Undertaking to agree to abide by the News Access Rules. The IOC will send the Undertaking to the confirmed ENR organisations who must return it to the IOC by the prescribed deadline. Exact dates will be shared once the News Access Rules for LA28 are finalised by the IOC. |
| 5 | Week commencing 18 October 2027 – PRESS BY NAME starts NOCs distribute the Olympic Press Accreditation Manual and related materials, received from LA28, to the approved ENR organisations along with their E quota. |
| 6 | 18 February 2028 – PRESS BY NAME ends NOCs must submit Press by Name accreditation applications for ENRs to LA28 along with their “E” quota by the deadline. |
| 7 | February to March 2028 LA28 verifies Press by Name accreditation applications submitted by NOCs for ENR organisations. |
| 8 | April 2028 The LA28 Accreditation Department is responsible for producing and distributing pre-valid Olympic Identity and Accreditation Cards (OIAC) to National Olympic Committees (NOCs), who then forward them to their ENR accredited organisations. Prior to distribution, ENR organisations must have signed the Undertaking. |
| 9 | 14 to 30 July 2028 Olympic Games LA28. |

## Sports Specialists Quota

As previously outlined in this document, sports specialist journalists and photographers are normally accredited through their respective NOC.

The IOC, however, reserves an additional quota of sport specialist accreditations for NOCs with late qualifying football teams, as well as a limited quota for sport specialist journalists or photographers recommended by the relevant International Federation that have not been allocated accreditation by their NOC. These accreditations are primarily distributed to International Federations whose sports are located in co-host cities, most notably FIFA, but may also include the FEI (Equestrian), World Sailing and some late team sport qualifiers. The IOC, in collaboration with LA28, will further consider separate allocations for additional sports outside of LA, including softball and canoe slalom in Oklahoma City.

For LA28, the International Federation will serve as the Responsible Organisation for these Es and EPs accreditations. LA28 will oversee the accreditation process in accordance with procedures established for other stakeholders. The proposed timetable is provided below.

| Step | Description |
| --- | --- |
| 1 | November 2026 The IOC notifies the selected IFs of their sport specialist media quota and outlines the process and deadlines. |
| 2 | Week commencing 18 January 2027 – PRESS BY NUMBER Press by Number information and additional press related documents to be sent to the selected IFs with their sport specialist quota. LA28 ACR and PRS to liaise with SPT on the communication channels with the respective IFs that are granted quota. IFs should encourage their sports specialists to seek their accreditation allocation from their respective NOC. The preference for quota allocation is via the NOC rather than the IF. |
| 3 | Selected IFs gather requests from their sport specialists who have been unable to secure accreditation allocation through their NOC. The LA28 Accreditation team identifies any duplicates between the NOC and IF lists. IFs should provide the OCOG Press Operations generic email for sport specialists' general inquiries such as reserving accommodation. Both IFs and LA28 must ensure sport specialists know press accommodation timelines and have access to published press manuals. |
| 4 | 12 February 2027 – PRESS BY NUMBER ends Deadline for IFs to submit their Press by Number forms to LA28 for their sport specialist media |
| 5 | Week commencing 18 October 2027 – PRESS BY NAME starts LA28 distributes the Press by Name Accreditation Manual and related information to each IF that has an allocation of sport specialists accreditations. |
| 6 | 18 February 2028 – PRESS BY NAME ends IFs follow the standard Press by Name process and deadlines and submit the data to LA28 on behalf of their individual sport specialists. |
| 7 | April 2028 LA28 Accreditation Department will produce and distribute the pre-valid Olympic Identity and Accreditation Cards (OIAC) directly to the IFs. IFs are responsible for distributing the Pre-Valid Cards to their individual sport specialists. |
| 8 | 14 to 30 July 2028 Olympic Games LA28. |

Qualifications may impact the IFs’ ability to meet the Press by Number deadline, especially for team sports. The LA28 Accreditation team should anticipate IFs updating organisation lists through and beyond the Press by Name deadline, similar to NOCs. Managing these updates falls under the Accreditation Team’s duties. Designating IFs as the Responsible Organisation will streamline the sport specialist accreditation process.

## IF Journalist (Es) and Photographer (EPs)

Separate from the sport specialists’ accreditations, the IOC allocates one Es and one EPs accreditation to each IF to assist the IF in the written and photographic coverage of their sport. Sports with multiple disciplines, or sports which operate in multiple venues, will be allocated more than one Es and EPs.

These accreditations and corresponding entitlements are strictly for journalists and photographers working on an exclusive basis for the IF to assist in sourcing material for the IF’s own editorial purposes such as federation magazines, newsletters and websites.

Accredited IF journalists and photographers will be granted access to the MPC and all relevant venues, including training areas, where their respective sports (across all disciplines) are held. According to the capacities of the press areas, IFs’ journalists and photographers might be given tickets to access the Opening and Closing Ceremonies.

As per the IOC rules and the Photographers Undertaking and Code of Conduct, IF photographers may not sell or share photos with third parties, agencies or news organisations.

| Step | Description |
| --- | --- |
| 1 | From October 2026 The IOC notifies the IFs regarding their allocation of Es (IF staff sports specific journalist) and EPs accreditations (IF staff sports specific photographer) |
| 2 | LA28 informs the IFs about the relevant press publications and press accommodation process. |
| 3 | September 2027 International Federations are to submit to the IOC the list of their staff accredited with Es and EPs. |
| 4 | Week commencing 18 October 2027 – PRESS BY NAME starts LA28 distributes the Press by Name Accreditation Manual and related information to each IF (name supplied by the IOC in the Master Database). |
| 5 | 18 February 2028 – PRESS BY NAME ends IFs to submit the Press By Name applications to LA28. |
| 6 | April 2028 LA28 Accreditation Department will produce and distribute the pre-valid Olympic Identity and Accreditation Cards (OIAC) directly to the IFs. |
| 7 | 14 to 30 July 2028 Olympic Games LA28. |

## Organisations not included in the NOC Quotas

The IOC directly allocates E category accreditations for:

The IOC recognised world news agencies:

- Agence France-Presse (AFP)

- The Associated Press (AP)

- Reuters Limited

- Xinhua News Agency.

The host national agency of the host country (not applicable for LA28).

The official photographic agency of the IOC/LA28.

International news organisations that do not fall within the territory of any NOC including former IOC Young Reporters who wish to cover the Games.

Olympic publications specializing in covering the Olympic Games only.

Non-media rights-holding radio and/or television news organisations (ENRs) in consultation with the NOCs (see detailed process in this document).

IF staff journalist and photographer (via the IF).

The IOC retains the authority to add any qualified organisations or representatives to this group at its discretion, provided they meet the established criteria and conditions. LA28 is responsible for distributing press accreditation forms and related guidelines to each organisation within these categories, following the same process as for the NOCs.

| Step | Description |
| --- | --- |
| 1 | March / April 2026 The IOC negotiates accreditation quotas with AFP, AP, Reuters, Xinhua News Agency as well as the IOC official photo agency. This timing enables these agencies to have priority access to reserve accommodation with LA28 ahead of the reservation period communicated to all media organisations. The IOC, at its discretion, confirms accreditation quotas with other international agencies, former Young Reporters, etc. for which it will be the Responsible Organisation. LA28 should send the Press Services and Facilities Guide, Rate Card Guide, Press Accommodation Guide and Customs and Freight Forwarding Guide to the major agencies when published and to all other directly accredited organisations. |
| 2 | The IOC informs LA28 of the quota (and category/ies) allocated to each organisation with the contact details |
| 3 | Week commencing 18 October 2027 – PRESS BY NAME starts LA28 distributes the Press by Name Accreditation Manual and related information directly to the organisations at the same time as the Press by Name information is sent to National Olympic Committees. |
| 4 | 18 February 2028 – PRESS BY NAME ends Deadline for organisations to return the Press by Name accreditation applications within the required deadline. LA28 reviews and confirms the data on the Press by Name accreditations. |
| 5 | April 2028 LA28 Accreditation Department will produce and distribute the pre-valid OIAC. |
| 6 | 14 to 30 July 2028 Olympic Games LA28. |

##### Distribution of OIAC Cards to Media

The OCOG is responsible for distributing all pre-valid OIAC to accredited press organisations and individuals. This process includes:

To all NOCs, who are then responsible for distributing to their national press including non-MRH as approved by the IOC.

To all IOC-recognised world news agencies directly accredited by the IOC.

To all international news organisations directly accredited by the IOC.

To all IFs, who are then responsible for distributing to the IF staff journalists/photographers, and where relevant to the sports specialists/individuals/freelancers directly accredited through the IF sport-specialist allocation.

This must be done in accordance with the timetable established by the IOC and the OCOG.

The OCOG is responsible for routinely submitting complete updates of the press accreditation database to the IOC upon request, for review throughout the press by number process until the conclusion of the Games.

# Co-Host Cities

## Allocation of Ex and EPx accreditations for Football and Co-Host Cities

The Football events will be covered by E, EP, Es and EPs accredited press as with all other sports.

However, in recognition of the fact that football will be held in multiple cities, the IOC proposes to allocate a limited quantity of Ex and EPx accreditations for local and national football press who would not normally receive accreditations through the USOPC allocation.

For the LA28 Games this will apply also to sports being hosted in Oklahoma City (Canoeing slalom and Softball).

This is intended to reduce pressure on the USOPC accreditation allocation and enables local press in these key cities to attend Olympic events, without the burden upon the Organising Committee of considering them within the official press quota for press accommodation, tribune seats, venue media facilities and MPC etc.

The proposed quota, per venue, and allocation procedure will be discussed in detail with the IOC, LA28 press operations and the USOPC.

Based on previous Games experiences, the following process is proposed:

The quotas, per venue, once proposed by LA28 and the USOPC and agreed by the IOC, will be allocated by the USOPC in close coordination with LA28 Press Operations.

They will be given Ex or EPx accreditation.

Ex/EPx accreditations for football will be a mix of single venue and multiple venue access (to be discussed). These accreditations will not provide access to the MPC, Opening and Closing Ceremonies, other football events in Los Angeles, (TBC if it will include the Football Finals), or any other competition venues in Los Angeles.

The Ex/EPx accreditations will be allocated to the USOPC for them to distribute as with the normal accreditation process.  However, they will not be included in the quota allocation of 6,000.

# Working Procedures

4.1     IOC Master E Accreditation tracking database

Continuing with the successful working relationship and procedures used at previous Games, the IOC will maintain a Master E Accreditation database which will be shared regularly with LA28 to monitor the status of all E allocations throughout the process.

This Excel database will track E allocations for NOCs as well as the other key clients including the IOC-Recognised world news agencies, Host National News Agency (if appointed), international news organisations and other organisations directly accredited by the IOC, sport specialists outside the NOC quotas, IF staff journalists and photographers and a summary for Non-Media Rights-Holding Broadcasters.

A separate database will be maintained for tracking the ENR accreditations.

The IOC is responsible for updating both databases and sending regular updates to LA28.  LA28 Accreditation will keep all master files and records.

##### Master E Accreditation tracking database

| Tab | Heading | Details | RO |
| --- | --- | --- | --- |
| 1 | IOC Summary | Current quota allocation for all stakeholders | IOC |
| 2 | NOC Allocation | NOC allocations, including subsequent 2nd, 3rd 4th allocations | NOC |
| 3 | IOC-Recognised world news agencies | Agence France-Presse, Associated Press, Reuters and Xinhua News Agency as the recognised international agency, the Host National News Agency for LA28 (if appointed) and the official photographic agency of the IOC. | IOC |
| 4 | International News Organisations | International News Organisations or individuals not included in the NOC quota. Examples of organisations which may be included under this category are the European Photo Agency, AIPS, former Young Reporters etc. Olympic specialist organisations would be listed under this category if accredited. | IOC |
| 5 | Sport Specialists not included in NOC quota | Sport Specialists recommended by the International Federations and approved by the IOC but not included in NOC quota. The Responsible Organisation will be the IF, unless informed otherwise. | IF |
| 6 | International Federations (IF staff journalist and photographer) | International Federations’ allocation of Es journalists and EPs photographers | IF |
| 7 | IOC Miscellaneous | Contingency allocation | IOC |
| 8 | Non-Media Rights- Holding Broadcasters (ENRs) | Accredited non-media rights-holding broadcasters (this will only contain the current numbers. A separate detailed ENR database will be kept) | IOC |

* RO = Responsible Organisation

##### 4.2. 	Working Languages

##### Policy

For the Olympic Games LA28 the working language should be as follows:

| Type of correspondence | Language/s |
| --- | --- |
| Correspondence between the IOC and LA28 | English |
| Official correspondence from the IOC to the NOCs on press accreditation matters | English, French, Spanish |
| Official correspondence from the IOC to the ENRs on matters of accreditation | English, French, Spanish |
| Accreditation documentation on the IOC website | English, French |

##### Publications

It is recommended that the following guides are published in the following languages:  (French versions to be discussed for the guides listed as English only)

| Type of correspondence | Language/s |
| --- | --- |
| Press by Number forms and Manual | English, French , Spanish |
| Press by Name Manual and related information | English, French , Spanish |
| Press Services and Facilities Guide | English |
| Press Accommodation Guide | English |
| Press Rate Card | English |
| Customs and Freight Forwarding Guide | English |

Acronyms

| Acronyms | Definition |
| --- | --- |
| AFP | Agence France-Presse |
| AP | The Associated Press |
| LA28 | Los Angeles Organising Committee for the Olympic and Paralympic Games |
| USOPC | United States Olympic and Paralympic Committee |
| ENR / Non-MRH | Accredited Non-Media Rights-Holding Television and Radio Broadcaster |
| IF | International Sporting Federation |
| IOC | International Olympic Committee |
| IOPP | International Olympic Photo Pool |
| MPC | Main Press Centre |
| NOC | National Olympic Committee |
| NOPP | National Olympic Photo Pool |
| OBS | Olympic Broadcasting Services |
| OCOG | Organising Committee for the Olympic Games |
| OIAC | Olympic Identity and Accreditation Card |
| WPB | World Press Briefing |
| RO | Responsible Organisation |

Annexes

- The IOC Guidelines for LA28 will be made available in 2027.  To view the Photographers Undertaking and the News Access Rules from the previous Summer Olympic Games in Paris 2024 and other Games related documents, please consult the following link:

- https://olympics.com/ioc/documents/olympic-games/paris-2024-olympic-games

The Press Accreditation process and timelines are also outlined on www.olympics.com via the following link:

https://olympics.com/ioc/accred2024

The Olympic rings, typography, pictograms, photographs and other assets featured in these guidelines are the property of the International Olympic Committee.

© 2021 International Olympic Committee

All Rights Reserved.

Maison Olympique – CH-1007 Lausanne / Switzerland

www.olympic.org