| LA28 - Media Registration - a streamlined and transparent process |  |
| --- | --- |

| Date: | 12 Mar 2026 |
| --- | --- |
| Participants: | LA28 : Martyn, Lauren Deloitte: David G, Chris S, Llorenc IOC: Lucia, Emma, Troy, Randi |
| Minute taker: | AI (review: Randi) Technology and Information Department |
| Objective: | Media Portal – press accreditation transparency |

Generated by AI.

Meeting notes:

- Press Accreditation Portal Development and Timeline: the need for a new, centralised press accreditation portal for the LA28 Games, emphasising the August launch deadline, the rationale for the system, and the urgency due to prior announcements to NOCs.

  - Rationale for Centralised Portal: IOC/Lucia explained that the IOC currently lacks visibility into how NOCs manage press accreditation after quotas are allocated, leading to transparency and reputational issues; the new portal aims to standardise and centralise the application process for all NOCs and media worldwide.

  - Timeline and Deadlines: The group confirmed that quotas are communicated to the NOCs in July, the portal must launch in August, and the expression of interest phase runs until 30 October, after which the press by number process begins (5 Oct); exact August dates are to be confirmed and communicated to the group.

  - Stakeholder Responsibilities: The IOC defines the initial process and requirements, NOCs are responsible to execute and manage the request for interest, while LA28 ACR take over from the press by number phase; Deloitte/Chris requested a clear process flow to delineate responsibilities.

  - Urgency and Lack of Backup Plan: The IOC/Lucia emphasised that the IOC has already announced the portal to NOCs and is committed to launching it, with no backup plan in place; the team agreed on the need to accelerate process mapping and technical discovery to meet the August deadline.

- Process Flow and Data Management for Accreditation: The group discussed the detailed workflow for press accreditation, including the expression of interest, press by number, and the handling of data at each stage, focusing on integration, data custody, and technical challenges.

  - Expression of Interest Phase: LA28/Martyn described the expression of interest as an open form where media organisations and freelancers indicate their intent to apply for accreditation, with NOCs responsible for managing and prioritising applicants according to their quotas.

  - Press by Number Phase: Martyn and OH explained that after the expression of interest, NOCs use the press by number process to allocate their quotas to specific organisations, with the IOC retaining visibility but not interfering unless controversies arise.

  - Data Integration and Workflow: The team discussed the potential for integrating the expression of interest data with the accreditation system, noting that while organisational data could be reused, individual data should not be collected too early due to changes and privacy concerns.

  - Data Archiving and Validation: IOC/Lucia requested that all application data be archived for reference throughout the Games, enabling the IOC to verify claims and resolve disputes; IOC/Emma and LA28/Martyn highlighted the need for additional data fields and validation steps at later stages.

- Technical and Security Considerations: Deloitte/Chris, IOC/Emma, and LA28/Martyn raised concerns about technical implementation, security, and potential misuse of the public portal, emphasising the need for robust process mapping and stakeholder input to address these challenges.

  - Security Risks of Public Portal: Deloitte/Chris highlighted risks such as unauthorised access if the application link is widely shared, and the need for mechanisms to authenticate applicants and prevent abuse, especially compared to the previous, more controlled Excel-based process.

  - Process Mapping and Requirements Gathering: The team agreed to prioritise mapping the end-to-end process, gathering requirements from all stakeholders, and clarifying technical and business needs before proceeding with system design.

  - Integration with Existing Systems: LA28/Martyn and the IOC/Emma discussed the importance of ensuring that the new portal can interface with existing accreditation and quota management systems, and that manual processes may still be required as a fallback for certain phases.

- Next Steps and Action Items: The group, agreed to accelerate the process mapping, clarify deadlines, and schedule in-person and remote workshops to finalise requirements and address outstanding questions before the August launch.

  - Process Mapping Assignment: Deloitte/Chris and LA28/Martyn agreed to facilitate process mapping sessions, with input from IOC representatives and technical teams, to visually document the workflow and clarify roles and responsibilities.

  - Timeline Clarification: The IOC committed to providing the group with exact dates for quota communication, portal launch, and submission deadlines to enable effective back-planning.

  - Workshop Planning: The group planned to hold both in-person and remote workshops, involving all key stakeholders, to iterate on requirements, address technical and process challenges, and ensure alignment ahead of the August deadline.

Follow-up tasks:

- Process Mapping for Media Accreditation Portal: Map the end-to-end process flow for the media accreditation portal, clearly distinguishing responsibilities and integration points between IOC, NOCs, and the LA28, and prepare a visual representation for collaborative review. (Deloitte, LA28 ACR)

- Provision of Key Timeline Dates: Provide the exact key dates for the August launch and subsequent deadlines for the media accreditation process to the technical and process teams to enable backward planning and scheduling. (IOC)

- Requirements Gathering for Portal Design: Gather and share a comprehensive set of requirements for the media accreditation portal, including business needs, data fields, and process expectations, to inform the technical solution design. (IOC/Lucia, Emma, LA28/Martyn)

- Workshop Scheduling for Process Discovery: Schedule and conduct an in-person or hybrid workshop to collaboratively map the process, clarify roles, and address technical and process concerns for the media accreditation portal implementation. (Chris Spinello, Llorenc Aguila, Martyn, Randi, Lucia)