| Media Portal – Prototype demo/presentation |  |
| --- | --- |

| Date: | 12 Mar 2026 |
| --- | --- |
| Participants: | LA28 : Martyn, Amy, Lauren Deloitte: Ken, Llorenc, Damien IOC: Lucia, Emma, Troy, Randi |
| Minute taker: | AI (reviewed by Randi) Technology and Information Department |
| Objective: | Media Portal – Prototype demo/presentation |

Generated by AI.

Prototype links and information distributed by Deloitte/Ken 2026-04-16:  2026-04-16 monkey-test-guide.docx (DISCUS folder: MRP - Media Request Portal).

Meeting notes:

- Prototype Demonstration and Feedback Process: Deloitte/Ken led a walkthrough of the new press registration portal prototype, others providing feedback on features, usability, and terminology, and agreeing on a rapid feedback and iteration cycle for further development.

- Prototype Overview and Access: Deloitte/Ken introduced the prototype for the press registration portal, explaining its purpose to streamline the accreditation process and reduce reliance on traditional requirements documents. The prototype was shared with the group, and participants discussed their experiences accessing and navigating it, noting some technical issues with submission and access.

- Terminology and Naming Conventions: IOC/Lucia requested that all references to 'media' be changed to 'press' throughout the portal, and the group discussed whether to use 'expression of interest' or 'registration' in the portal's naming. The consensus was to use 'press registration portal' (PRP) for clarity and consistency.

- Form Fields and Customization: The group discussed the consolidation of form fields to accommodate different NOCs' needs, with Emma confirming ongoing work to finalize the required fields. The group agreed that while customization for each NOC is technically possible, the initial version should focus on a standardized set of fields, with future flexibility considered for later iterations.

- Workflow and User Roles: Deloitte/Ken explained the workflow for applicants, NOC admins, OCOG admins, and IOC admins, including the ability for admins to 'act as a user' for support purposes. The group clarified the visibility and responsibilities of each role, emphasizing the need for audit trails and clear separation of functions between NOCs, OCOG, and IOC.

- Feedback and Iteration Process: Participants agreed to provide feedback on the prototype via email or the DISCUS platform, with Ken and Damien committing to rapid turnaround on updates. The group planned to finalize field lists and provide consolidated feedback by of next week, aiming for a quick iteration cycle before the next meeting.

- Process Design and Workflow Decisions: The team discussed key process decisions for the press registration portal, such as application submission, approval, rejection, audit trails, and the handling of quotas and deadlines.

- Application Submission and Confirmation: The group agreed that applicants should receive an automatic email confirmation upon submitting their expression of interest, with no immediate interaction required from the NOC at this stage. This provides applicants with proof of submission and reduces unnecessary communication.

- Approval, Rejection, and Communication: It was decided that NOCs should manage approvals and rejections internally, with no automated rejection emails sent from the system to applicants. Sensitive communications, especially rejections, should be handled offline by NOCs in their own language and style to avoid political or reputational issues.

- Audit Trail and Data Retention: The IOC emphasized the importance of maintaining a complete audit trail for all applications, including rejected ones, to ensure transparency and accountability. Deloitte/Ken confirmed that the system will log all actions and prevent deletion of applicant records, allowing the IOC to review the history in case of disputes.

- Quota Management and Allocation: The workflow for managing and allocating quotas was discussed, including the need for consolidated views showing requests, allocations, and totals per organization. The group requested enhancements to make quota management more intuitive and to prevent over-allocation.

- Deadlines and Submission Controls: The team agreed on having a global deadline for public submissions, with the option for NOCs to invite or fast-track organizations after the deadline. The ability to reopen submissions for specific NOCs after the deadline was also discussed as a necessary feature.

- Special Cases: ENR, IF, and Paralympic Processes: The group addressed the handling of ENR (non-rights broadcasters), International Federations (IFs), and Paralympic processes, outlining requirements for prioritization, data integration, and alignment with Olympic workflows.

  - ENR Application and Prioritization: The process for ENR nominations was discussed, with NOCs submitting prioritized lists to the IOC, which then decides on slot allocations. The need for clear ranking functionality and easy access to organization details for review was highlighted.

  - IF Workflow and Integration: Deloitte/Ken explained that the IF workflow would mirror the NOC process but with adjustments for the smaller number of IFs involved. The group discussed the need to handle organizations that may have multiple types of accreditations across different timelines.

  - Paralympic and NPC Considerations: The group discussed whether the IPC would use the same portal for expression of interest, noting that while the processes are similar, the forms and requirements may differ. The consensus was to build the tool to accommodate both Olympic and Paralympic needs, with the option to disable certain features as required.

- Technical Support, Onboarding, and Language Support: The group discussed plans for technical support, user onboarding, and language options for the portal and related documentation.

- Technical Support Structure: Deloitte/Ken, Llorenc confirmed that the D.TEC team and existing accreditation support teams will handle technical support for the portal, with established mechanisms for issue resolution.

- User Onboarding Process: LA28/Martin outlined the process for onboarding NOC users, including gathering user lists, legal waivers, and setup procedures, mirroring the approach used for accreditation systems.

- Language Availability: The team discussed language requirements, agreeing to start with English, French, and Spanish for the portal and documentation, with further adjustments based on user feedback and organizational policies.

- Next Steps and Meeting Planning: The group agreed to coordinated next steps, including feedback collection, prototype updates, and scheduling the next meeting to review progress and address outstanding issues.

- Feedback and Iteration Timeline: Participants agreed to provide consolidated feedback on the prototype and field lists by early next week, enabling Deloitte to implement updates before the next meeting.

- Scheduling the Next Meeting: The group decided to set a placeholder for the next meeting at the end of the following week, with flexibility to adjust based on participants' availability and progress on the prototype.

Follow-up tasks:

- Prototype Feedback and Field Consolidation: Send consolidated feedback and finalized fields for the press registration portal prototype to Deloitte/Ken for review and integration. (Fields: Emma)

- Prototype Technical Issue Resolution: Investigate and resolve the issue preventing users from submitting requests in the prototype portal, ensuring the submit button functions correctly. (Damien Antoine Chauvet)

- Stakeholder Questions and Comments Submission (stakeholder-questions.docx (DISCUS)): Add comments and responses to the stakeholder questions directly to the files on discus or provide an offline copy if access is unavailable. (all)

- Next Meeting Scheduling: Send a placeholder for the next meeting, aiming for the beginning of the last week of April, to review the updated prototype and feedback. (IOC/Randi)

- Language Policy Confirmation: Confirm with the team the minimum language requirements for the press registration portal and related manuals and guides. (LA28 TEC/Lauren)

- User Onboarding Process Planning: Gather the list of NOC users with the help of NCS and existing lists, coordinate legal waivers, and plan user onboarding for the portal. Same/similar process as ACR onboarding (LA28 ACR)

- Press Registration Portal Naming: Relabel the portal as "Press Registration Portal" (PRP) and update internal and public-facing terminology accordingly. (Deloitte/Ken)